## Sheet1
Activity | Business Owner | Procurement | GRC | InfoSec | Legal | Privacy | IT | Exec Mgmt
Initiate vendor request | R/A | C | I | - | - | - | - | -
Initial screening | C | R | A | - | - | - | - | -
Criticality / risk tiering | C | I | R/A | C | - | C | - | -
Due diligence collection | I | - | R/A | R | - | C | - | -
Risk assessment & rating | I | - | R/A | R | C | R | - | I
Contract risk clauses | C | R | C | C | R/A | C | - | -
Approval — Low/Medium tier | I | I | R/A | C | - | - | - | I
Approval — High tier / exceptions | I | I | R | C | - | - | - | A
Access provisioning | C | - | I | C | - | - | R/A | -
Ongoing monitoring | R | - | A | C | - | - | I | I
Periodic reassessment | C | - | R/A | C | - | C | - | I
Offboarding / access revocation | C | - | A | I | C | - | R | -
R = Responsible
A = Accountable
C = Consulted
I = Informed
- = No formal RACI assignment