## Sheet1
Vendor Findings Register
ID | Vendor | Requirement | Condition | Evidence | Risk | Severity | Recommendation | Owner | Due | Status | Escalation
F-001 | NorthPeak | Logical access control assurance (T1) | SOC 2 scope covers infrastructure only; logical access pushed to CUECs | EV-01 | Production access controls unevidenced | Medium | Request scoped evidence for logical access controls; verify ApexBridge-side CUEC obligations | VP Engineering | 60 days | Open | GRC-managed
F-002 | Corestack | Credential management (T1, privileged access) | No defined or evidenced secrets management | EV-03, EV-04, EV-05 | Unauthorized production deployment | High | Obtain specific secrets management detail and operating evidence; consider interim permission scope reduction | VP Engineering | 30 days | Open | Exec Mgmt
F-003 | Meridian Pay | Fourth-party assurance | Primary payment subprocessor named but unassessed | EV-08 | Unassessed dependency in payment flow | Medium | Obtain subprocessor assurance evidence at or before renewal | Finance Director | 90 days | Open | GRC-managed
F-004 | Guardline | Evidence currency monitoring | ApexBridge held expired certificate; no refresh trigger existed | EV-06 | Stale assurance position undetected | Low | Add certificate expiry tracking to the vendor monitoring cadence | GRC | Next cycle | Open | None
F-005 | Ferrow Analytics | Assessment completion (pending tier) | Questionnaire incomplete on retention, subcontractors, access management | EV-11 | Tier cannot be finalized; customer data access unassessed | Medium | Complete outstanding sections as precondition to tier finalization | Dir. Product Analytics | 45 days | Open | GRC-managed
OBS-01 | Brightloop | Data handling (T3) | No formal security documentation beyond public trust page | EV-10 | Minimal — no system access, contact data only | Observation | No action; adequate for tier. Revisit if scope changes | Marketing Director | n/a | Closed | None