## Sheet1
vendor remediation risk treatment tracker
ID | Vendor | Risk | Sev | Treatment | Action | Risk Owner | Action Owner | Target | Compensating Control | Required Evidence | Status | Acceptance Req'd | Approver | Escalation | Closure Criteria | Validation
F-002 | Corestack | Unauthorized production deployment via unmanaged credentials | High | Mitigate | Vendor: managed secrets storage + rotation. ApexBridge: scoped service account, approval-gated promotion | VP Engineering | Eng. Platform Lead / Corestack AM | Interim 10d; vendor fix next quarter | Permission restriction + deployment alerting (end-dated to vendor fix) | Implementation evidence of rotation; confirmation interim control liftable | In Progress | No | Exec Mgmt (interim plan) | Escalated | Rotation evidence validated by GRC + interim control safely lifted | Pending
F-006 | Corestack | Unknown vulnerabilities in current platform version | Medium | Mitigate | Obtain pen test covering current platform version, within 12 months, incl. high-severity remediation status | VP Engineering | GRC Analyst (coordination) | 60 days | None | Pen test report with scope and date confirmation | Awaiting Vendor | No | Head of GRC | GRC-managed | Report received, scope confirmed, high findings remediated or rationalized | Not started
F-003 | Meridian Pay | Unassessed dependency in payment flow | Medium | Mitigate + Transfer | Request processor assurance evidence; where unavailable, contract amendment for subprocessor notification and obligation pass-through | Finance Director | Legal (amendment) / GRC (evidence) | 90 days | Tokenization (existing, not time-bound) | Assurance evidence OR executed amendment | In Progress | No | Head of GRC | GRC-managed | Evidence reviewed or amendment executed | Not started
F-005 | Ferrow Analytics | Raw customer data access with unassessed controls; tier unfinalized | Medium | Mitigate | Complete questionnaire sections (retention, subcontractors, access mgmt); finalize tier on receipt | Dir. Product Analytics | Dir. Product Analytics | 45 days | None | Completed questionnaire sections | Awaiting Vendor | No | Head of GRC | GRC-managed | Sections complete, tier assigned, resulting findings raised separately | Not started
F-001 | NorthPeak | Logical access controls not covered by provided SOC 2 | Medium | Accept | Accept with conditions on basis of equivalent ISO 27001 evidence and bounded CUEC exposure | VP Engineering | GRC (CUEC verification) | Review in 12 months | ApexBridge tenant-level access controls (per CUECs) | ISO cert scope statement; CUEC verification record | Risk Accepted | Yes | Head of GRC | Within authority | Not closed — reviewed at expiry or on material service change | Complete
F-004 | Guardline | Assurance position may go stale undetected across vendor population | Low | Mitigate | Add evidence expiry tracking to inventory and monitoring cadence; flag at 60 days pre-expiry | GRC | GRC | Next review cycle | None | Populated expiry fields; flagging mechanism demonstrated | Open | No | Head of GRC | None | Expiry fields populated for T1/T2; flagging demonstrated | Not started
OBS-01 | Brightloop | Minimal — no system access, contact data only | Obs | None | No action; adequate for tier | Marketing Director | n/a | n/a | n/a | n/a | Closed | No | n/a | None | Closed on Day 4 as observation; revisit if scope changes | n/a