APEXBRIDGE TECHNOLOGIES

TPRM MANAGEMENT REPORT

Reporting period: Initial TPRM cycle
Prepared by: GRC Analyst
For: Executive Management
Status: Simulated project artifact

EXECUTIVE SUMMARY

The initial TPRM assessment cycle is complete. A governed, risk-tiered vendor population now exists where none did previously, and six vendors have undergone detailed assessment and evidence review.

The programme is functioning, but this first cycle has surfaced two Tier 1 vendors where ApexBridge cannot currently evidence its risk position, and one active security incident.

Two items require management decision this period:

- The Solvane security incident combined with its lapsed certification and overdue reassessment.

- The slipped remediation date on Corestack's privileged-access finding.

PORTFOLIO OVERVIEW

Measure: Total third parties in scope
Value: 47

Measure: Tier distribution
Value: T1: 6, T2: 11, T3: 18, T4: 12

Measure: Vendors with current risk assessment
Value: 31 / 47 (66%)

Measure: Tier 1 vendors with current assessment
Value: 5 / 6 (83%)

Measure: Required evidence current
Value: 15 / 17 (88%)

Measure: Open findings
Value: 5

Measure: Overdue findings
Value: 2 (one High, one Medium)

Measure: Active risk acceptances
Value: 1 (Tier 1, conditions outstanding)

Measure: Reassessment triggers this period
Value: 3

Measure: Vendors with incomplete risk data
Value: 1

KEY RISK THEMES

- Assurance Evidence Ageing on Critical Vendors

Two of six Tier 1 vendors lack current independent assurance. Solvane's ISO certificate lapsed six weeks ago, and Corestack has never provided independent assurance.

Until F-004's expiry-tracking remediation completes, ApexBridge has no systematic mechanism to detect this.

- Concentration Around Critical Infrastructure

NorthPeak hosts the entire production environment and Corestack sits in the deployment path for every release.

Neither has a viable short-term alternative.

This is not a finding. It is a structural characteristic worth stating because a failure at either vendor would be a business continuity event rather than simply a vendor issue.

- Remediation Delivery Slipping on the Highest-Risk Item

Corestack's F-002 is 12 days overdue.

Exposure has not increased because the interim compensating control is holding, but the pattern warrants attention in a first cycle.

- Subprocessor Visibility Remains Partial

Meridian Pay has disclosed subprocessors and notified a new one. The notification obligation is working, but none of the named subprocessors has been assessed.

Fourth-party risk is visible but not yet evaluated.

- Monitoring Data Incomplete for One Data-Bearing Vendor

Ferrow Analytics has confirmed access to a raw customer dataset with no assigned tier and no monitoring baseline.

Action is in progress and within timeline, but it remains a known blind spot.

MANAGEMENT ATTENTION REQUIRED

Item: Solvane incident and lapsed assurance

Decision for management: Whether to invoke contractual rights, whether to prepare payroll contingency, and employee notification posture.

Analyst recommendation: Priority reassessment on receipt of the incident report. Maintain daily status until scope is known. Do not restate the risk rating without evidence.

Item: Corestack F-002 slippage

Decision for management: Whether to accept the revised vendor date or require an escalated commitment.

Analyst recommendation: Accept a revised date only with the continued interim control and monthly reporting. Treat further slippage as a treatment decision, not a scheduling decision.

Item: NorthPeak RA-001 conditions

Decision for management: Whether the acceptance stands with a condition unmet.

Analyst recommendation: Complete CUEC verification within 14 days. Re-open the acceptance if it is not completed, in accordance with its own terms.

Item: Assessment coverage at 66%

Decision for management: Whether to resource a second assessment wave or extend the assessment cadence.

Analyst recommendation: Prioritise the remaining Tier 1 and Tier 2 population. Tier 3 and Tier 4 coverage can reasonably follow in the next cycle.

Item: Concentration on NorthPeak and Corestack

Decision for management: Whether contingency planning is warranted for either vendor.

Analyst recommendation: Raise the matter for consideration in business continuity planning. This is a strategic question, not a TPRM finding.

GOVERNANCE NOTE

The recommendations above are decision support.

Risk acceptance, resource allocation, and strategic vendor decisions remain with management and the named risk owners.